# Public Health Programme Timeline

Edit the SETTINGS and EVENTS tables, save the document, then run render_timeline.py. Column names are case-insensitive; several common alternatives are accepted.

# SETTINGS

| Setting | Value |
| --- | --- |
| Title | Public Health Programme Redesign |
| Subtitle | Illustrative milestones, workstreams and approval stages |
| Height | 620px |
| Orientation | bottom |
| Stack | yes |

# EVENTS

| Event ID | Start Date | End Date | Title | Description | Category | Track | Colour |
| --- | --- | --- | --- | --- | --- | --- | --- |
| e01 | 2026-01-12 | 2026-02-20 | Discovery and evidence review | Review the existing programme, student feedback and assessment pattern. | Planning | Programme | #bfdbfe |
| e02 | 2026-02-02 | 2026-03-13 | Module mapping workshops | Map learning outcomes, content and assessments across modules. | Curriculum | Academic design | #bbf7d0 |
| e03 | 2026-03-02 | 2026-04-03 | Assessment redesign | Develop a smaller, coherent programme-level assessment pattern. | Assessment | Academic design | #fde68a |
| e04 | 2026-04-15 |  | Stage 3 review | Submit the redesign for the third programme approval stage. | Approval | Governance | #fecaca |
| e05 | 2026-04-20 | 2026-05-29 | Learning design prototypes | Prototype online and intensive-mode learning activities. | Development | Digital education | #ddd6fe |
| e06 | 2026-06-17 |  | Stage 4 approval | Final institutional approval milestone. | Approval | Governance | #fecaca |
| e07 | 2026-07-01 | 2027-05-31 | Content production | Produce, review and quality-assure module materials. | Development | Digital education | #ddd6fe |
| e08 | 2027-09-27 |  | Revised programme launches | First teaching week for the redesigned programme. | Delivery | Programme | #a7f3d0 |

# Column guidance

Event ID: Optional unique identifier. A value is generated if blank.

Start Date: Required. Use YYYY-MM-DD, DD/MM/YYYY, or a written date such as 15 April 2026.

End Date: Optional. When supplied, the item is displayed as a date range.

Title: Required event label.

Description: Optional text displayed in the event tooltip.

Category: Optional filter category.

Track: Optional timeline lane/group.

Colour: Optional CSS colour name, hex, rgb() or hsl().

URL: Optional http/https link.